| - AP | - Action | - Progress | - Further Update |
| --- | --- | --- | --- |
| - Actions outstanding from February 2015 |  |  |  |
| - 001/100215 - 002/100215 | - Board members to complete Skills Matrix by 27/2/15. - Secretariat to conduct skills gap analysis. | - Initial matrix(es) received 12/3/15. - LNA completed - Second iteration completed 31/10/15 - LNA updated – further learning needs to be considered individually. - To be reviewed once revised ToR agreed in June 2016. | - Review/ update underway. Updated document will be shared with Board members during Autumn 2016. - ON-GOING |
| - Actions from 9 March 2016 |  |  |  |
| - 010/090316 - Link to AP 05/150616 | - Sub-group for contract re-tendering to be established. DfE Officials to provide a timeline for consideration to facilitate decision making. | - To be discussed once ToR and composition of 3 sub-groups complete / agreed. | - Timeline drafted for consideration re establishing a sub-committee. - Agenda item 12 for 7 September 2016. - ON-GOING – Move to AP05/150616 |
| - Actions from 15 June 2016 |  |  |  |
| - 01/150616 | - Commentary to AP008/090316 to be re-worded to state that proposed chairs had been discussed via email exchange 17-18/03/16. | - Secretariat to action | - Amendment made immediately following 15 June Board meeting. - COMPLETE |
| - 02/150616 | - JR to work with the Chair to draft a report on the key achievements of the Board for general circulation to membership and other interested parties. This to be considered at the next Board. |  | - Report drafted for consideration. - Agenda item 5 for 7 September 2016. - COMPLETE |
| - 03/150616 | - The Role and Person Specification for the TPSPB Chair to be added to the updated TPSPB Terms of Reference. |  | - Updated Terms of Reference, including the Chair Role and Person Specification as an annex, circulated with the 15 June minutes on 21/06/16. - COMPLETE |
| - 04/150616 | - The Department to ensure that the TPSPB are played in (from an early stage) to discussions on the re-tender project when work is underway. | - Contract team advised. Governance / secretariat team minful of requirement and to ensure requirement is met. | - TPSPB will consider whether /when it wishes to establish a re-tender sub-committee, and its supporting Terms of Reference. - Agenda item 12 for 7 September 2016. - COMPLETE |
| - 05/150616 - Link to AP 010/090316 | - The Department to set out a provisional timetable for the re-tender project, for consideration at the next Board. |  | - Timeline drafted for consideration re establishing a sub-committee. - Agenda item 12 for 7 September 2016 - ON-GOING PENDING DECISION |
| - 06/150616 | - DH to feed back to MDC project colleagues in TP (and the Department) about the Board’s concerns regarding how/to whom to target communications within organisations. | - Update regarding MDC communications covered in the Engagement Report. | - On-going requirement to provide the Board with project updates to both the relevant sub-committee(s) and the Board is noted. - COMPLETE |
| - 07/150616 | - TP to provide regular MDC updates to the Board. DH to provide a brief update and field questions at the next Board meeting. | - Updates included in administration narrative report. |  |
| - 08/150616 | - Engagement Report to include an update on progress against the project to contact members to determine their channel of choice for receiving P60s. | - Report author advised of requirement. | - Update included in September report. - COMPLETE |
| - 09/150616 | - The Department to re-send the email response to the pension input period (PiP) query, raised at the last meeting, to all Board members. |  | - Circulated with the 15 June 2016 minutes on 21 June 2016. - COMPLETE |
| - 10/150616 | - The next Administration Report to include an update on progress against the Annual Service Return submission deadline of 7 July. | - Report author advised of requirement. | - Update include in September report. - COMPLETE |
| - 11/150616 | - An explanatory note providing more detail regarding outcome meaures 2 and 3 to be circulated to the Board. | - Contract manager to work with TP colleagues to draft. | - To be addressed via a “teach-in” session on 7 September 2016. - COMPLETE |
| - 12/150616 | - The Department to confirm how the process regarding how accounts are qualified in schools in the maintained sectors operates. | - Work on this was parked whilst the Annual Report and Accounts process was finalised. DfE’s Finance and Commercial Group have been approached for advice. | - Update scheduled for the December Board meeting. - ON-GOING |
| - 13/150616 | - Governance Statement : page 29 para 4:20. The word “financial” to be removed as the assurance process is wider | - Report author advised of requirement. | - Changes made 16 June 2016. - COMPLETE |
| - 14/150616 | - 1. Secretariat to liaise with the Board regarding the date and venue for the inaugural sub-committee meetings, and co-ordinate the meetings. - 2. The Department to consider who should attend to support. | - Meetings took place on 26 July 2016 in Sanctury Buildings, London. - Officials from the Contract Management and Finance teams (assigned as points of contact) attended to support each sub-group. - Dates agreed for subsequent meetings in 2016/2017. | - Notes on outcomes / actions circulated to all Board members for information on 5 August 2016. - Agenda item 3 for 7 September 2016. - COMPLETE |
| - 15/150616 | - In light of the comments and reservations expressed by the Board on P60s, the Department and TP will consider further and update the Board at the next meeting. | - Update included in Engagement Report. | - Agenda item 9 for 7 September 2016. - COMPLETE |